## Project Plan
Project Name: | [Name]
Report Date | [Date]
Project Status | On track
Completed | 27%
Tasks | Assigned To | Priority | Status
Set kick-off meeting | Alessandro B. |  | Complete
Agree on objectives | Franco C. | ★ | Complete
Detailed Reqs. | Giacomo S. |  | Complete
Hardward Reqs. | Giacomo S. | ★ | Overdue
Final Resource Plan | Giacomo S. |  | In progress
Staffing | Alessandro B. | ★ | In progress
Techincal Reqs. | Franco C. |  | Not started
Testing | Massimo P. | ★ | Not started
Dev. Complete | Giacomo S. | ★ | Not started
Hardware Config. | Alessandro B. |  | Not started
System Testing | Massimo P. | ★ | Not started
Launch

## Notes
Task Table
Tasks | Assigned To | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-03 | 1 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-12 | 5 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-16 | 2015-09-17 | 1 | In progress
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
Testing | Kennedy K. | 2015-09-24 | 2015-10-02 | 8 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-06 | 2015-10-09 | 3 | Not started
Launch |  | 2015-10-09 | 2015-10-10 | 1
Percentage of Tasks Complete
Complete | 27.27%
Overdue | 9.091%
In progress | 18.18%
Not Started | 45.45%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4

## Project Budget
Project Budget Sheet
Project :
Start Date:
| Labor |  | Materials |  |  |  | FIXED |  |  |  | BALANCE
Task | HR | €/HR | UNITS | €/UNITS | TRAVEL | EQUP/SPACE |  | MISC | BUDGET | ACTUAL | UNDER/OVER
Project | [8 empty] | 600 | 1440 | -840
Task | 8 | 15 | 100 | 5 |  |  | 50 |  | 200 | 670 | -470
Task | 8 | 15 |  |  |  |  | 100 |  | 300 | 220 | 80
Task |  |  | 50 | 11 |  |  |  |  | 100 | 550 | -450
SubTask | [8 empty] | 0 | 0 | 0
SubTask | [8 empty] | 0 | 0 | 0
SubTask | [8 empty] | 0 | 0 | 0
SubTask | [8 empty] | 0 | 0 | 0
Task | [8 empty] | 0 | 0 | 0
Task | [8 empty] | 0 | 0 | 0
SUBTOTAL |  | 240 |  | 1050 | 0 |  | 150 | 0 | 600 | 1440 | -840
Project | [8 empty] | 0 | 0 | 0
Task | [8 empty] | 0 |  | 0
Task | [8 empty] | 0 |  | 0
Task | [8 empty] | 0 |  | 0
SubTask | [8 empty] | 0 |  | 0
SubTask | [8 empty] | 0 |  | 0
Task | [8 empty] | 0 |  | 0
Subtotal |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## Gannt Chart
Task Name | Start | End | Duration (days)
Task 1 | 2015-01-16 | 2015-01-21 | 5
Task 2 | 2015-01-22 | 2015-01-23 | 1
Task 3 | 2015-01-22 | 2015-01-28 | 6
Task 4 | 2015-01-27 | 2015-01-29 | 2
Task 5 | 2015-01-28 | 2015-02-04 | 7
Task 6 | 2015-02-05 | 2015-02-09 | 4
Task 7 | 2015-01-28 | 2015-02-05 | 8
Task 8 | 2015-02-04 | 2015-02-06 | 2
Task 9 | 2015-02-07 | 2015-02-10 | 3
Task 10 | 2015-02-09 | 2015-02-12 | 3
Task 11 | 2015-02-11 | 2015-02-14 | 3
Task 12 | 2015-02-15 | 2015-02-17 | 2
`

## Issue Tracker
Issue Tracker Template
Project:
Start Date:
Issue No | Status | Issue Description | Category | Priority | Assignee | Raised By | Open | Close | Comments
1 | Fixed | Saving throws an error | Type 1 | HIGH | Giovanni | Anna | 2015-08-01 | 2015-08-01
2 | Active | Can't export PDF | Type 2 | HIGH | Giovanni | Teresa | 2015-08-04
3 | Active | User cannot print | Type 2 | HIGH | Giovanni | Roberta | 2015-08-04
4 | Active | Schema update | Type 3 | LOW | Melissa | Dario | 2015-08-14
5
6
7
8
9
10
11
12
13
14
15

## Risk Template
Project Risk Template
Task Status/Priority |  | High | Medium | Low | Total | % of Total
Closed |  | 0 | 1 | 0 | 1 | 25%
Work in Progress |  | 2 | 0 | 0 | 2 | 50%
Behind |  | 0 | 1 | 0 | 1 | 25%
Not Started |  | 0 | 0 | 0 | 0 | 0%
Total |  | 2 | 2 | 0 | 4
ID | Description | Status | Assignee | Risk Level | Deadline
1 | API Design | Closed | Giovanni | Medium | 2015-09-18
2 | API Development | Behind | Marta | Medium | 2015-08-31
3 | API Testing | Work in Progress | Gilberto | High | 2015-07-14
4 | Deploy | Work in Progress | Roberto | High | 2015-09-08
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Timeline Template
Task Name | Start | End | Duration (days)
Task 1 | 2015-01-16 | 2015-01-21 | 5
Task 2 | 2015-01-22 | 2015-01-23 | 1
Task 3 | 2015-01-22 | 2015-01-28 | 6
Task 4 | 2015-01-27 | 2015-01-29 | 2
Task 5 | 2015-01-28 | 2014-02-04 | 7
Task 6 | 2015-02-05 | 2015-02-09 | 4
Task 7 | 2015-01-28 | 2015-02-05 | 8
Task 8 | 2015-02-04 | 2015-02-06 | 2
Task 9 | 2015-02-07 | 2015-02-10 | 3
Task 10 | 2015-02-09 | 2015-02-12 | 3
Task 11 | 2015-02-11 | 2015-02-14 | 3
Task 12 | 2015-02-15 | 2015-02-17 | 2

## Timesheet
Timesheet
Employee:
[5 empty] | Week of: | 2015-08-30
Day of the Week | Start | Finish | Regulars Hours | Overtime | Sick | Vacation | Holiday | Other | Total Hours
2015-08-30 | 8:00 | 17:00 | 9 | 2 |  |  |  |  | 11
2015-08-31 |  |  | 0 | [5 empty] | 0
2015-09-01 |  |  | 0 | [5 empty] | 0
2015-09-02 |  |  | 0 | [5 empty] | 0
2015-09-02 |  |  | 0 | [5 empty] | 0
2015-09-03 |  |  | 0 | [5 empty] | 0
2015-09-04 |  |  | 0 | [5 empty] | 0
Total Hours |  |  | 9 | 2 | 0 | 0 | 0 | 0 | 11
Rate/HR |  |  | 15 | 25
Total Pay: |  |  | 135 | 50 | 0 | 0 | 0 | 0 | 185

## To Do List
To Do List
Task | Status | Priority | Due Date | Assignee | Notes
Task 1 | Completed | High | 2015-08-21 | Gigi